## MOM
MOM 13-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Menu Configuration | 3 | 2016-01-13 | 2016-01-13 | AM | 0 | TO DO
|  |  | MDN Analysis and Code Review | 24 | 2016-01-12 | -688103 | AS | 20 | WIP | Structural Analysis of MDN(Flow)
2 | Taiga | P M T | Implement the rest services for timeline and consume on taiga | 6 | 2016-01-13 | 2016-01-13 | ASC | 0 | TO DO
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO
4 | Ascott | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-13 | NJ | 0 | TO DO | 2 Points related to push park in todo section , 2 Points in progress and 1 point park in waiting for input
6 | Rewardz | Mobile App(Frontend) | Share button is not working |  | 2016-01-13 | 2016-01-13 | NJ | 0 | TO DO | Parked in TO DO Section of trello.
|  |  | Api Documentation. | 8 | 2016-01-13 | 2016-01-13 | NP | 0 | TO DO
7 | IGNITE | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-13 | NJ | 0 | TO DO | 2 Point Park in TO DO Section and 1 Point Park in progress section of trello
8 | Learning | Mobile/Web | Best Practices in Going through Ionic Framework | 4 | 2016-01-13 | 2016-01-13 | MK | 0 | TO DO
|  |  | Express Website Tutorial Project 2 | 2 | 2016-01-13 | 2016-01-13 | AM | 0 | TO DO
MOM 14-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Menu Configuration | 3 | 2016-01-13 | 2016-01-14 | AM | 50 | WIP | Confusion in eligibility Configuration
|  |  | MDN Analysis and Code Review | 24 | 2016-01-12 | -688103 | AS | 50 | WIP | Structural Analysis of MDN(Flow)
2 | Taiga | P M T | Implement the rest services for timeline and consume on taiga | 6 | 2016-01-13 | 2016-01-14 | ASC | 40 | WIP | Rest services are 90% completion just one error for resolve
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO
4 | Ascott | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-14 | NJ | 0 | TO DO | 2 Points related to push park in todo section , 2 Points in progress and 1 point park in waiting for input
6 | Rewardz | Mobile App(Frontend) | Share button is not working |  | 2016-01-13 | 2016-01-14 | NJ | 0 | TO DO | Parked in TO DO Section of trello.
|  |  | Api Documentation. | 8+4 | 2016-01-13 | 2016-01-14 | NP | 70 | WIP
7 | IGNITE | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-13 | NJ | 0 | TO DO | 2 Point Park in TO DO Section and 1 Point Park in progress section of trello
8 | Learning | Mobile/Web | Best Practices in Going through Ionic Framework | 4 | 2016-01-13 | 2016-01-13 | MK | 100 | DONE
|  |  | Express Website Tutorial Project 2 | 2 | 2016-01-13 | 2016-01-13 | AM | 50 | WIP
|  |  | Estimation and Project Setup and api documentation | 8 | 2016-01-14 | 2016-01-14 | MK | 0 | TO DO
MOM 15-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Menu Configuration | 3 | 2016-01-13 | 2016-01-14 | AM | 50 | WIP | Confusion in eligibility Configuration
|  |  | MDN Analysis and Code Review | 24 | 2016-01-12 | -688103 | AS | 50 | WIP | Structural Analysis of MDN(Flow)
2 | Taiga | P M T | Implement the rest services for timeline and consume on taiga | 6 | 2016-01-13 | 2016-01-14 | ASC | 50 | WIP | Rest services are 90% completion just one error for resolve & started the frontend customization
|  |  | Gulp and code understanding of taiga | 8 | 2016-01-15 | 2016-01-15 | AM | 0 | TO DO
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO
4 | Ascott | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-14 | NJ | 0 | TO DO | 2 Points related to push park in todo section , 2 Points in progress and 1 point park in waiting for input
|  |  | Checkin validation for date/attended scenario & alert changes for ques submit | 4 | 2016-01-14 | 2015-01-14 | NK | 100 | Done | Code Pushed
6 | Rewardz | Mobile App(Frontend) | Share button is not working |  | 2016-01-13 | 2016-01-14 | NJ | 0 | TO DO | Parked in TO DO Section of trello.
|  |  | Api Documentation. | 8+4 | 2016-01-13 | 2016-01-15 | NP | 70 | WIP | Need to map DTO and Response
7 | IGNITE | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-13 | NJ | 0 | TO DO | 2 Point Park in TO DO Section and 1 Point Park in progress section of trello
|  |  | Unit Testing | 2 | 2016-01-15 | 2016-01-15 | NK | 0 | TO DO
8 | Learning | Mobile/Web | Best Practices in Going through Ionic Framework | 4 | 2016-01-13 | 2016-01-13 | MK | 100 | DONE
|  |  | Express Website Tutorial Project 2 | 2 | 2016-01-13 | 2016-01-13 | AM | 100 | Done
|  |  | Estimation and Project Setup and api documentation | 8 | 2016-01-14 | 2016-01-14 | MK | 100 | DONE
|  |  | Login Page design, impl. Valid and consume web service | 8 | 2016-01-15 | 2016-01-15 | MK | 0 | TO DO
MOM 16-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Menu Configuration | 3 | 2016-01-13 | 2016-01-14 | AM | 50 | WIP | Confusion in eligibility Configuration
|  |  | MDN Analysis and Code Review | 24 | 2016-01-12 | -688102 | AS | 70 | WIP | Structural Analysis of MDN(Flow)
2 | Taiga | P M T | Implement the rest services for timeline and consume on taiga | 6 | 2016-01-13 | 2016-01-16 | ASC | 60 | WIP | Rest services are 90% completion just one error for resolve & started the frontend customization with coffee script & jade
|  |  | Gulp and code understanding of taiga | 8 | 2016-01-15 | 2016-01-16 | AM | 20 | WIP
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO
4 | Ascott | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-16 | NJ | 0 | TO DO | 2 Points related to push park in todo section , 2 Points in progress and 1 point park in waiting for input
|  |  | Checkin validation for date/attended scenario & alert changes for ques submit | 4 | 2016-01-14 | 2015-01-14 | NP | 100 | Done | Code Pushed
|  |  | Checkin api error handling | 2 | 2016-01-16 | 2016-01-16 | NP | 0 | TO DO
6 | Rewardz | Mobile App(Frontend) | Share button is not working |  | 2016-01-13 | 2016-01-14 | NJ | 0 | TO DO | Parked in TO DO Section of trello.
|  |  | Api Documentation. | 8+4 | 2016-01-13 | 2016-01-15 | NP | 70 | WIP | Need to map DTO and Response
|  |  | Checkin api error handling | 2 | 2016-01-16 | 2016-01-16 | NP | 0 | TO DO
7 | IGNITE | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-13 | NJ | 0 | TO DO | 2 Point Park in TO DO Section and 1 Point Park in progress section of trello
|  |  | Unit Testing | 2 | 2016-01-15 | 2016-01-15 | NP | 100 | DONE
|  |  | Checkin api error handling | 2 | 2016-01-16 | 2016-01-16 | NP | 0 | TO DO
8 | Learning | Mobile/Web | Best Practices in Going through Ionic Framework | 4 | 2016-01-13 | 2016-01-13 | MK | 100 | DONE
|  |  | Express Website Tutorial Project 2 | 2 | 2016-01-13 | 2016-01-13 | AM | 100 | Done
|  |  | Estimation and Project Setup and api documentation | 8 | 2016-01-14 | 2016-01-14 | MK | 100 | DONE
|  |  | Login Page design, impl. Valid and consume web service | 8 | 2016-01-15 | 2016-01-15 | MK | 50 | WIP
|  |  | Forgot password & page design | 4 | 2016-01-16 | 2016-01-16 | MK | 0 | TO DO
MOM 19-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Menu Configuration | 3 | 2016-01-13 | 2016-01-14 | AM | 50 | WIP | Confusion in eligibility Configuration
|  |  | MDN Analysis and Code Review | 24 | 2016-01-12 | -688102 | AS | 100 | Done | Structural Analysis of MDN(Flow)
|  |  | Going through Authorization(Resolve Property) | 8 | 2016-01-18 | 2016-01-19 | AS | 30 | WIP
2 | Taiga | P M T | Implement the rest services for timeline and consume on taiga | 6 | 2016-01-13 | 2016-01-16 | ASC | 60 | WIP | Rest services are 90% completion just one error for resolve & started the frontend customization with coffee script & jade
|  |  | Gulp and code understanding of taiga in frontend | 8 | 2016-01-15 | 2016-01-16 | AM | 100 | Done
|  |  | Design the timeline interface | 8 | 2016-01-18 | 2016-01-18 | AM | 100 | Done
|  |  | Implement the functionality for timeline page in frontend | 8 | 2016-01-19 | 2016-01-19 | ASC | 0 | TO DO
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO
4 | Ascott | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-16 | NJ | 0 | TO DO | 2 Points related to push park in todo section , 2 Points in progress and 1 point park in waiting for input
|  |  | Checkin validation for date/attended scenario & alert changes for ques submit | 4 | 2016-01-14 | 2015-01-14 | NP | 100 | Done | Code Pushed
|  |  | Checkin api error handling | 2 | 2016-01-16 | 2016-01-16 | NP | 0 | TO DO
|  |  | Push Notification Refinement | 2 | 2016-01-19 | 2016-01-19 | NP | 0 | TO DO
6 | Rewardz | Mobile App(Frontend) | Share button is not working |  | 2016-01-13 | 2016-01-14 | NJ | 0 | TO DO | Parked in TO DO Section of trello.
|  |  | Api Documentation. | 8+4 | 2016-01-13 | 2016-01-15 | NP | 70 | WIP | Need to map DTO and Response
|  |  | Checkin api error handling | 2 | 2016-01-16 | 2016-01-16 | NP | 0 | TO DO
|  |  | Push Notification Refinement | 2 | 2016-01-19 | 2016-01-19 | NP | 0 | TO DO
7 | IGNITE | Mobile App(Frontend) | Push Notification Issue |  | 2016-01-13 | 2016-01-13 | NJ | 0 | TO DO | 2 Point Park in TO DO Section and 1 Point Park in progress section of trello
|  |  | Unit Testing | 2 | 2016-01-15 | 2016-01-15 | NP | 100 | DONE
|  |  | Checkin api error handling | 2 | 2016-01-16 | 2016-01-16 | NP | 0 | TO DO
|  |  | Push Notification Refinement | 2 | 2016-01-19 | 2016-01-19 | NP | 0 | TO DO
8 | Learning | Mobile/Web | Best Practices in Going through Ionic Framework | 4 | 2016-01-13 | 2016-01-13 | MK | 100 | DONE
|  |  | Express Website Tutorial Project 2 | 2 | 2016-01-13 | 2016-01-13 | AM | 100 | Done
|  |  | Estimation and Project Setup and api documentation | 8 | 2016-01-14 | 2016-01-14 | MK | 100 | DONE
|  |  | Login Page design, impl. Valid and consume web service | 8 | 2016-01-15 | 2016-01-15 | MK | 100 | DONE
|  |  | Forgot password & page design | 4 | 2016-01-16 | 2016-01-16 | MK | 100 | done
|  |  | Consume service for forget password | 8 | 2016-01-19 | 2016-01-19 | MK | 0 | TO DO
MOM 20-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Menu Configuration | 3 | 2016-01-13 | 2016-01-14 | AM | 50 | WIP | Confusion in eligibility Configuration
|  |  | MDN Analysis and Code Review | 24 | 2016-01-12 | -688102 | AS | 100 | Done | Structural Analysis of MDN(Flow)
|  |  | Going through Authorization(Resolve Property) | 8 | 2016-01-18 | 2016-01-20 | AS | 30 | WIP
2 | Taiga | P M T | Implement the rest services for timeline and consume on taiga | 6 | 2016-01-20 | 2016-01-20 | ASC | 60 | WIP | Continue.....
|  |  | Implement the functionality for timeline page in frontend | 8 | 2016-01-19 | 2016-01-19 | ASC | 50 | TO DO | Hold due to errors in service of timeline taiga
|  |  | Resolve the error in services of timeline | 7 | 2016-01-20 | 2016-01-20 | ASC | 0 | TO DO
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO
4 | EmPerks | Mobile App(Frontend) | Project Setup (optimum , zurich) | 1 | 2016-01-20 | 2016-01-20 | NP | 0 | TO DO
|  |  | Push Notification Issue | 5 | 2016-01-20 | 2016-01-20 | NP | 0 | TO DO | Point Park in Todo Section of trello has 4 checklist
5 | Learning | Mobile/Web | Consume service for forget password | 8 | 2016-01-19 | 2016-01-19 | MK | 0 | TO DO | Hold due to auth key services
|  |  | Home Page Design | 8 | 2016-01-19 | 2016-01-19 | MK | 100 | Done
|  |  | Consume the services for home page and design | 8 | 2016-01-20 | 2016-01-20 | MK | 0 | TO DO
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-01-20 | AM | 0 | TO DO
MOM 21-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Menu Configuration | 3 | 2016-01-13 | 2016-01-14 | AM | 50 | WIP | Confusion in eligibility Configuration
|  |  | Going through Authorization(Resolve Property) | 8 | 2016-01-18 | 2016-01-20 | AS | 100 | Done
|  |  | Eligibility Conf. Screen Design impl. | 8 | 2016-01-21 | 2016-01-21 | AS/AM | 0 | TO DO
2 | Taiga | P M T | Implement the functionality for timeline page in frontend | 6 | 2016-01-19 | 2016-01-21 | ASC | 50 | WIP | Continue ....
|  |  | Resolve the error in services of timeline | 2 | 2016-01-20 | 2016-01-21 | ASC | 50 | WIP | post and get working problem in put and delete operation(resolving..)
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO
4 | EmPerks | Mobile App(Frontend) | Project Setup (optimum , zurich) | 1 | 2016-01-20 | 2016-01-20 | NP | 100 | Done
|  |  | Testing | 8 | 2016-01-21 | 2016-01-21 | NP | 0 | TO DO
5 | Learning | Mobile/Web | Consume service for forget password | 8 | 2016-01-19 | 2016-01-19 | MK | 100 | Done | Hold due to auth key services
|  |  | Consume the services for home page and design | 8 | 2016-01-20 | 2016-01-20 | MK | 0 | TO DO | Hold
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-01-21 | AM | 30 | WIP | HOLD
6 | C.P Jobsite | Mobile App(Frontend) | Resolve 4 points in Mail | 8 | 2016-01-21 | 2016-01-21 | MK | 0 | TO DO
MOM 22-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Eligibility Conf. Screen Design impl. | 8 | 2016-01-21 | 2016-01-22 | AS | 50 | WIP
|  |  | Resolve MDN 7 Issues | 4 | 2016-01-22 | 2016-01-22 | AM | 0 | TO DO
2 | Taiga | P M T | Implement the functionality for timeline page in frontend | 4 | 2016-01-19 | 2016-01-22 | ASC | 70 | WIP | Continue ....
|  |  | Resolve the error in services of timeline | 4 | 2016-01-20 | 2016-01-22 | ASC | 60 | WIP | Resolving the error in service for getting tasks for particular project
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO
4 | EmPerks | Mobile App(Frontend) | Testing | 8 | 2016-01-21 | 2016-01-21 | NP | 100 | DONE
5 | Learning | Mobile/Web | Consume service for forget password | 8 | 2016-01-19 | 2016-01-19 | MK | 100 | Done | Hold due to auth key services
|  |  | Consume the services for home page and design | 8 | 2016-01-20 | 2016-01-20 | MK | 0 | TO DO | Hold
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-01-21 | AM | 30 | WIP | HOLD
6 | C.P Jobsite | Mobile App(Frontend) | Resolve 4 points in Mail | 8 | 2016-01-21 | 2016-01-21 | MK | 0 | TO DO
7 | Avanti | Mobile App(Frontend) | Back Button for android | 4 | 2016-01-22 | 2016-01-22 | NP | 0 | TO DO
8 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-22 | AM | 0 | TO DO
MOM 23-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Eligibility Conf. Screen Design impl. | 8 | 2016-01-21 | 2016-01-22 | AS | 50 | WIP | Today Status Not Clear Absent
|  |  | Resolve MDN 7 Issues | 4 | 2016-01-22 | 2016-01-25 | AM | 60 | WIP | Need to test all poitns demo at 1 pm
2 | Taiga | P M T | Implement the functionality for timeline page in frontend | 4 | 2016-01-19 | 2016-01-22 | ASC | 70 | WIP | Continue ...., Today Status Not Clear Absent
|  |  | Resolve the error in services of timeline | 4 | 2016-01-20 | 2016-01-22 | ASC | 60 | WIP | Resolving the error in service for getting tasks for particular project , Today Status Not Clear Absent
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO , Need to discuss these points with Nikhil;
4 | EmPerks | Mobile App(Frontend) | Event attendiong issue in all emperk build | 4 | 2016-01-25 | 2016-01-25 | AM |  | TO DO
5 | Learning | Mobile/Web | Consume service for forget password | 8 | 2016-01-19 | 2016-01-19 | MK | 100 | Done | Hold due to auth key services
|  |  | Consume the services for home page and design | 8 | 2016-01-20 | 2016-01-20 | MK | 0 | TO DO | Hold
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-01-21 | AM | 30 | WIP | HOLD
6 | C.P Jobsite | Mobile App(Frontend) | Resolve 4 points in Mail | 8 + 4 | 2016-01-21 | 2016-01-25 | MK | 0 | WIP | Need to implement translate api in overall project
7 | Avanti | Mobile App(Frontend) | Back Button for android | 4 | 2016-01-22 | 2016-01-22 | NP | 0 | TO DO | Today Status Not Clear Absent
8 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-22 | AM | 0 | TO DO | Need to dscuss its priority
MOM 27-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Eligibility Conf. Screen Design impl. | 8 | 2016-01-21 | 2016-01-22 | AS | 100 | Done
|  |  | Resolve MDN 7 Issues | 4 | 2016-01-22 | 2016-01-25 | AM | 60 | WIP | Need to test all poitns demo at 2 pm
|  |  | MDN Testing and client demo | 8 | 2016-01-27 | 2016-01-27 | AM | 0 | TO DO
2 | Taiga | P M T | Implement the functionality for timeline page in frontend | 4 | 2016-01-19 | 2016-01-22 | ASC | 70 | WIP | Continue ....,
|  |  | Resolve the error in services of timeline | 4 | 2016-01-20 | 2016-01-22 | ASC | 100 | Done | Resolving the error in service for getting tasks for particular project Done.
|  |  | Timeline Post and Date functionality | 4 | 2016-01-27 | 2016-01-27 | ASC | 0 | TO DO
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO , Need to discuss these points with Nikhil;
4 | EmPerks | Mobile App(Frontend) | Event attendiong issue in all emperk build | 4 | 2016-01-25 | 2016-01-25 | AM | 100 | Done | for testing..
|  |  | Performance & Trello point |  | 2016-01-27 | 2016-01-27 | NP | 0 | TO DO
5 | Learning | Mobile/Web | Consume service for forget password | 8 | 2016-01-19 | 2016-01-19 | MK | 100 | Done | Hold due to auth key services
|  |  | Consume the services for home page and design | 8 | 2016-01-20 | 2016-01-20 | MK | 0 | TO DO | Hold
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-01-21 | AM | 30 | WIP | HOLD
|  |  | Learning set up phone gap | 8 | 2016-01-27 | 2016-01-27 | AS | 0 | TO DO
|  |  | Category & subcategory of list | 16 | 2016-01-27 | 2016-01-28 | MK | 0 | TO DO
6 | C.P Jobsite | Mobile App(Frontend) | Resolve 4 points in Mail | 8 + 4 | 2016-01-21 | 2016-01-25 | MK | 100 | Done | Need to implement translate api in overall project
|  |  | Resolve 1 Trello issue | 4 | 2016-01-27 | 2016-01-27 | MK
7 | Avanti | Mobile App(Frontend) | Back Button for android | 4 | 2016-01-22 | 2016-01-22 | NP | 100 | Done | Today Status Not Clear Absent
8 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-22 | AM | 0 | TO DO | Hold
MOM 28-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Eligibility Conf. Screen Design impl. | 8 | 2016-01-21 | 2016-01-22 | AS | 100 | Done
|  |  | Resolve MDN 7 Issues | 4 | 2016-01-22 | 2016-01-25 | AM | 100 | Done
|  |  | MDN Testing and client demo | 8 | 2016-01-27 | 2016-01-27 | AM | 50 | WIP
|  |  | Customer service consumption and client demo | 8 | 2016-01-28 | 2016-01-28 | AM | 0 | TO DO | Task related to above
2 | Taiga | P M T | Implement the functionality for timeline page in frontend | 4 | 2016-01-19 | 2016-01-22 | ASC | 70 | WIP | Continue ....,
|  |  | Timeline Post and Date functionality | 7 | 2016-01-27 | 2016-01-28 | ASC | 50 | WIP
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO , Need to discuss these points with Nikhil;
4 | EmPerks | Mobile App(Frontend) | Event attendiong issue in all emperk build | 4 | 2016-01-25 | 2016-01-25 | AM | 100 | Done | for testing..
|  |  | Performance & Trello point | 8 | 2016-01-27 | 2016-01-27 | NP | 100 | Done | waiting for testing ....
|  |  | Redirect to dev like flab in Rewards,ignite and DBSchenker | 8 | 2016-01-28 | 2016-01-28 | NP | 0 | TO DO
5 | Learning | Mobile/Web | Consume service for forget password | 8 | 2016-01-19 | 2016-01-19 | MK | 100 | Done | Hold due to auth key services
|  |  | Consume the services for home page and design | 8 | 2016-01-20 | 2016-01-20 | MK | 0 | TO DO | Hold
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-01-21 | AM | 30 | WIP | HOLD
|  |  | Learning set up phone gap | 8 | 2016-01-27 | 2016-01-27 | AS | 100 | Done
|  |  | Category & subcategory of list | 16 | 2016-01-27 | 2016-01-28 | MK | 0 | TO DO | HOLD
|  |  | Run Cordova Project and understanding | 8 | 2016-01-28 | 2016-01-28 | AS | 0 | TO DO
6 | C.P Jobsite | Mobile App(Frontend) | Resolve 1 Trello issue | 4 | 2016-01-27 | 2016-01-27 | MK | 100 | Done
|  |  | Resolve Login Password issue | 4 | 2016-01-28 | 2016-01-28 | MK | 0 | TO DO
8 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-22 | AM | 0 | TO DO | Hold
MOM 29-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | Eligibility Conf. Screen Design impl. | 8 | 2016-01-21 | 2016-01-22 | AS | 100 | Done
|  |  | Resolve MDN 7 Issues | 4 | 2016-01-22 | 2016-01-25 | AM | 100 | Done
|  |  | MDN Testing and client demo | 8 | 2016-01-27 | 2016-01-27 | AM | 70 | WIP
|  |  | Customer service consumption and client demo | 8 | 2016-01-28 | 2016-01-28 | AM | 100 | Done | Task related to above
2 | Taiga | P M T | Implement the functionality for timeline page in frontend | 4 | 2016-01-19 | 2016-01-22 | ASC | 70 | WIP | Restructuring it with $scope of angular that was conflicting with coffee script
|  |  | Timeline Post and Date functionality | 7 | 2016-01-27 | 2016-01-28 | ASC | 60 | WIP | Resolving the Issue in service for posting tiemline
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO , Need to discuss these points with Nikhil;
4 | EmPerks | Mobile App(Frontend) | Redirect to dev like flab in Rewards,ignite and DBSchenker | 8 | 2016-01-28 | 2016-01-28 | NP | 100 | Done
|  |  | Testing & analysis | 8 | 29/01//2016 | 2016-01-29 | NP | 0 | TO DO
5 | Learning | Mobile/Web | Consume the services for home page and design | 8 | 2016-01-20 | 2016-01-29 | MK | 0 | TO DO
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-01-21 | AM | 30 | WIP | HOLD
|  |  | Learning set up phone gap | 8 | 2016-01-27 | 2016-01-27 | AS | 100 | Done
|  |  | Category & subcategory of list | 16 | 2016-01-27 | 2016-01-29 | MK | 0 | TO DO
|  |  | Run Cordova Project and understanding | 8 | 2016-01-28 | 2016-01-28 | AS | 30 | WIP
6 | C.P Jobsite | Mobile App(Frontend) | Resolve Login Password issue | 4 | 2016-01-28 | 2016-01-28 | MK | 100 | Done
7 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 50 | WIP | (50% work done on 28 Jan)
MOM 30-Jan-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | MDN | Web Projects(Frontend) | MDN Testing and client demo | 8 | 2016-01-27 | 2016-01-27 | AM | 100 | Done
|  |  | Customer service consumption and client demo | 8 | 2016-01-28 | 2016-01-28 | AM | 100 | Done | Task related to above
2 | Taiga | P M T | Implement the functionality for timeline page in frontend | 4 | 2016-01-19 | 2016-01-30 | ASC | 80 | WIP
|  |  | Timeline Post and Date functionality | 7 | 2016-01-27 | 2016-01-30 | ASC | 90 | WIP
|  |  | Implement Retrieval service for posted timeline and implement it on frontend | 7 | 2016-01-30 | 2016-01-30 | ASC | 0 | TO DO
3 | Easy Futbol | Mobile App(Frontend) |  | 0 |  |  | MK |  | WIN | 4 POINTS PARK IN WAITING FOR INPUT IN TRELLO , Need to discuss these points with Nikhil;
4 | EmPerks | Mobile App(Frontend) | Testing & analysis | 8 | 2016-01-29 | 2016-01-29 | NP | 100 | Done
|  |  | Resolve the Trello Points | 8 | 2016-01-30 | 2016-01-30 | NP | 0 | TO DO
5 | Learning | Mobile/Web | Consume the services for home page and design | 8 | 2016-01-20 | 2016-01-29 | MK | 0 | TO DO | Absent
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-01-30 | AM | 30 | WIP
|  |  | Category & subcategory of list | 16 | 2016-01-27 | 2016-01-29 | MK | 0 | TO DO | Absent
|  |  | Run Cordova Project and understanding | 8 | 2016-01-28 | 2016-01-28 | AS | 100 | Done
7 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | WIP | Some Points Pending from SJ side
MOM 01-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the functionality for timeline page in frontend | 4 | 2016-01-19 | 2016-01-30 | ASC | 80 | WIP
|  |  | Timeline Post and Date functionality | 7 | 2016-01-27 | 2016-01-30 | ASC | 100 | WIP
|  |  | Implement Retrieval service for posted timeline and implement it on frontend | 7 | 2016-01-30 | 2016-01-30 | ASC | 80 | TO DO | Resolving one issue in retrieval on frontend side
|  |  | Timeline extended functionality analysis and User Introduction in timeline | 8 | 2016-02-01 | 2016-02-01 | ASC | 0 | TO DO
2 | EmPerks | Mobile App(Frontend) | Resolve the Trello Points | 8 | 2016-01-30 | 2016-01-30 | NP | 50 | WIP | 1 point solved and 1 point pre solved within 3 point so 1 point remaining
|  |  | Resolve the 3 points | 8 | 2016-02-01 | 2016-02-01 | NP | 0 | TO DO
3 | Learning | Mobile/Web | Consume the services for home page and design | 8 | 2016-01-20 | 2016-02-01 | MK | 10 | WIP
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-02-01 | AM | 40 | WIP
|  |  | Category & subcategory of list | 16 | 2016-01-27 | 2016-02-01 | MK | 0 | TO DO
4 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | WIP | Some Points Pending from SJ side
5 | C P Jobsite | Mobile App(Frontend) | C P Jobsite analysis | 8 | 2016-02-01 | 2016-02-01 | AS | 0 | TO DO | Instead of this task ToDo Page design is assigned
MOM 02-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the functionality for timeline page in frontend | 4 | 2016-01-19 | 2016-01-30 | ASC | 80 | WIP
|  |  | Implement Retrieval service for posted timeline and implement it on frontend | 7 | 2016-01-30 | 2016-01-30 | ASC | 80 | WIP | Resolving one issue in retrieval on frontend side
|  |  | Timeline extended functionality analysis and User Introduction in timeline | 4 | 2016-02-01 | 2016-02-02 | ASC | 40 | WIP | Having a issue in updating the dbms table so below task was done and estimation has been sent
|  |  | Design of Timeline briefing Page | 8 | 2016-02-01 | 2016-02-01 | ASC | 100 | Done
|  |  | Writing a service for Timeline briefing page | 4 | 2016-01-02 | 2016-01-02 | ASC | 0 | TO DO
2 | EmPerks | Mobile App(Frontend) | Resolve the Trello Points | 8 | 2016-01-30 | 2016-01-30 | NP | 50 | WIP | 1 point solved and 1 point pre solved within 3 point so 1 point remaining
|  |  | Resolve the 3 points | 8 | 2016-02-01 | 2016-02-02 | NP | 0 | TO DO
3 | Learning | Mobile/Web | Consume the services for home page and design | 8 | 2016-01-20 | 2016-02-02 | MK | 100 | Done
|  |  | Node Js(User login system) | 8 | 2016-01-20 | 2016-02-02 | AM | 60 | WIP
|  |  | Category & subcategory of list | 16 | 2016-01-27 | 2016-02-02 | MK | 30 | WIP
|  |  | Implement NavBar functionalty on dashboard | 8 | 2016-02-02 | 2016-02-02 | MK | 0 | TODO
|  |  | AngularJs 2 | 8 | 2016-02-02 | 2016-02-02 | NP | 0 | TO DO
4 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | WIP | Some Points Pending from SJ side
5 | TO DO App | Mobile App(Frontend) | Dasign DashBoard | 8 | 2016-02-02 | 2016-02-02 | AS | 0 | TO DO
MOM 03-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the functionality for timeline page in frontend | 4 | 2016-01-19 | 2016-01-30 | ASC | 80 | WIP
|  |  | Implement Retrieval service for posted timeline and implement it on frontend | 7 | 2016-01-30 | 2016-01-30 | ASC | 80 | WIP | Resolving one issue in retrieval on frontend side
|  |  | Timeline extended functionality analysis and User Introduction in timeline | 8 | 2016-02-01 | 2016-02-02 | ASC | 100 | Done
|  |  | Writing a service for Timeline briefing page | 4 | 2016-01-02 | 2016-01-02 | ASC | 0 | TO DO | Hold
|  |  | Implement the Range for retrival in date on timeline | 7 | 2016-02-03 | 2016-02-03 | ASC | 0 | TO DO
2 | EmPerks | Mobile App(Frontend) | Resolve the Trello Points | 8 | 2016-01-30 | 2016-01-30 | NP | 50 | WIP | 1 point solved and 1 point pre solved within 3 point so 1 point remaining
|  |  | Resolve the 3 points | 8 | 2016-02-01 | 2016-02-03 | NP | 0 | WIP
3 | Learning | Mobile/Web | Node Js(User login system) | 8 | 2016-01-20 | 2016-02-02 | AM | 80 | WIP
|  |  | Category & subcategory of list | 16 | 2016-01-27 | 2016-02-02 | MK | 100 | Done
|  |  | Implement NavBar functionalty on dashboard | 8 | 2016-02-02 | 2016-02-02 | MK | 50 | WIP
|  |  | AngularJs 2 | 8 | 2016-02-02 | 2016-02-02 | NP | 20 | WIP
|  |  | Newest List Consume service,Detail Page Design all All Categories | 8 | 2016-02-03 | 407645 | MK | 0 | TODO
4 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | WIP | Some Points Pending from SJ side
5 | TO DO App | Mobile App(Frontend) | Design DashBoard | 8 | 2016-02-02 | 2016-02-02 | AS | 80 | WIP
|  |  | Task Update and Screen Design | 8 | 2016-02-03 | 2016-02-03 | AS | 0 | TO DO
MOM 04-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement Retrieval service for posted timeline and implement it on frontend | 7 | 2016-01-30 | 2016-01-30 | ASC | 80 | WIP | Resolving one issue in retrieval on frontend side
|  |  | Timeline extended functionality analysis and User Introduction in timeline | 8 | 2016-02-01 | 2016-02-02 | ASC | 100 | Done
|  |  | Writing a service for Timeline briefing page | 4 | 2016-01-02 | 2016-01-02 | ASC | 0 | TO DO | Hold
|  |  | Implement the Range for retrival in date on timeline | 7 | 2016-02-03 | 2016-02-04 | ASC | 80 | TO DO | Resolving one issue in retrieval on frontend side
2 | EmPerks | Mobile App(Frontend) | Resolve the Trello Points | 8 | 2016-01-30 | 2016-01-30 | NP | 50 | WIP | 1 point solved and 1 point pre solved within 3 point so 1 point remaining
|  |  | Resolve the 3 points | 8 | 2016-02-01 | 2016-02-04 | NP | 50 | WIP
|  |  | Add event in calender for reward | 8 | 2016-01-04 | 2016-01-04 | NP | 0 | WIP
3 | Learning | Mobile/Web | Node Js(User login system) | 8 | 2016-01-20 | 2016-02-04 | AM | 90 | WIP
|  |  | Implement NavBar functionalty on dashboard | 8 | 2016-02-02 | 2016-02-02 | MK | 50 | WIP | Hold
|  |  | AngularJs 2 | 8 | 2016-02-02 | 2016-02-02 | NP | 20 | WIP | Hold
|  |  | Newest List Consume service,Detail Page Design All Categories | 8 | 2016-02-03 | 407645 | MK | 0 | TODO | Hold
|  |  | Upderstand the sqlite & Implementation | 8 | 2016-02-04 | 2016-02-04 | AS | 0 | TO DO
4 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | WIP | Some Points Pending from SJ side
5 | TO DO App | Mobile App(Frontend) | Design DashBoard and Implementation | 8 | 2016-02-02 | 2016-02-02 | AS | 80 | WIP | Update Implementation
|  |  | Task Update and Screen Design | 8 | 2016-02-03 | 2016-02-03 | AS | 0 | TO DO
6 | Parent Blocked | Mobile App(Frontend) | Put the screens shot of error on trello & yesterday task | 8 | 2016-02-04 | 2016-02-04 | AS | 0 | TO DO
MOM 05-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement Retrieval service for posted timeline and implement it on frontend | 7 | 2016-01-30 | 2016-01-30 | ASC | 100 | Done
|  |  | Writing a service for Timeline briefing page | 4 | 2016-01-05 | 2016-01-05 | ASC | 0 | TO DO
|  |  | Implement the Range for retrival in date on timeline | 7 | 2016-02-03 | 2016-02-04 | ASC | 100 | Done
|  |  | Update in timeline | 8 | 2016-02-05 | 2016-02-05 | ASC | 0 | TO DO
2 | EmPerks | Mobile App(Frontend) | Resolve the Trello Points | 8 | 2016-01-30 | 2016-01-30 | NP | 50 | WIP | 1 point solved and 1 point pre solved within 3 point so 1 point remaining
|  |  | Resolve the 3 points | 8 | 2016-02-01 | 2016-02-04 | NP | 50 | WIP
|  |  | Add event in calender for reward | 8 | 2016-01-04 | 2016-01-04 | NP | 50 | WIP
3 | Learning | Mobile/Web | Node Js(User login system) | 8 | 2016-01-20 | 2016-02-04 | AM | 100 | Done
|  |  | Implement NavBar functionalty on dashboard | 8 | 2016-02-02 | 2016-02-02 | MK | 50 | WIP | Hold
|  |  | AngularJs 2 | 8 | 2016-02-02 | 2016-02-02 | NP | 20 | WIP | Hold
|  |  | Newest List Consume service,Detail Page Design All Categories | 8 | 2016-02-03 | 407645 | MK | 0 | TODO | Hold
|  |  | Upderstand the sqlite & Implementation | 8 | 2016-02-04 | 2016-02-04 | AS | 0 | TO DO | Hold
4 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | WIP | Some Points Pending from SJ side
5 | TO DO App | Mobile App(Frontend) | Design DashBoard and Implementation | 8 | 2016-02-02 | 2016-02-02 | AS | 100 | Done
|  |  | Task Update and Screen Design | 8 | 2016-02-03 | 2016-02-03 | AS | 100 | Done
|  |  | Design Modification in TODO App | 8 | 2016-02-05 | 2016-02-05 | AS | 0 | TO DO
6 | Parent Blocked | Mobile App(Frontend) | Put the screens shot of error on trello & yesterday task | 8 | 2016-02-04 | 2016-02-04 | MK | 100 | Done
|  |  | Estimate the project & Facebook Integration and analysis of pubnub api | 8 | 2016-02-05 | 2016-02-05 | MK | 0 | TO DO
7 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-06 | AM | 0 | TO DO
MOM 06-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Writing a service for Timeline briefing page(timesheet) | 4 | 2016-01-05 | 2016-01-06 | ASC | 30 | WIP
|  |  | Update in timeline | 8 | 2016-02-05 | 2016-02-05 | ASC | 100 | Done
2 | EmPerks | Mobile App(Frontend) | Resolve the Trello Points | 8 | 2016-01-30 | 2016-01-30 | NP | 50 | WIP | 1 point solved and 1 point pre solved within 3 point so 1 point remaining
|  |  | Resolve the 3 points | 8 | 2016-02-01 | 2016-02-04 | NP | 50 | WIP
|  |  | Add event in calender for reward | 8 | 2016-01-04 | 2016-01-04 | NP | 50 | WIP | (Absent)
3 | My Street | Mobile App/WEB(Frontend) | Resolve 11 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | WIP | Some Points Pending from SJ side
4 | TO DO App | Mobile App(Frontend) | Design Modification in TODO App | 8 | 2016-02-05 | 2016-02-06 | AS | 80 | WIP | Resolve the issue in design
5 | Parent Blocked | Mobile App(Frontend) | Replicate the issues and mapped on trello | 8 | 2016-02-05 | 2016-02-06 | MK | 100 | Done
6 | Chat Application | Mobile App(Frontend) | Estimate the project | 8 | 2016-02-05 | 2016-02-05 | MK | 100 | Done
|  |  | Analysis of pubnub api | 8 | 2016-02-06 | 2016-02-06 | MK | 0 | TO DO
7 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-06 | AM | 40 | WIP
MOM 08-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Writing a service for Timeline briefing page(timesheet) | 4 | 2016-01-05 | 2016-01-08 | ASC | 90 | WIP | Remaing task : Adding a field in models and make modification if any needed during implementation on frontEnd
|  |  | Update in timeline | 8 | 2016-02-05 | 2016-02-05 | ASC | 100 | Done
|  |  | Implement the timesheet service on frontEnd Taiga | 8 | 2016-02-08 | 2016-02-08 | ASC | 0 | TO DO
2 | EmPerks | Mobile App(Frontend) | Add event in calender for reward | 4 | 2016-01-04 | 2016-01-08 | NP | 50 | WIP | 8 Points on trello and working on 3 points
|  |  | Password based Redemption | 4 | 2016-01-08 | 2016-01-08 | NP | 0 | TO DO
|  |  | Reset Password | 1 | 2016-01-08 | 2016-01-08 | NP | 0 | TO DO
3 | My Street | Mobile App/WEB(Frontend) | Resolve 1 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | WIP | Apply validation on live deal pending from SJ side
4 | TO DO App | Mobile App(Frontend) | Design Modification in TODO App | 8 | 2016-02-05 | 2016-02-06 | AS | 100 | Done
5 | Parent Blocked | Mobile App(Frontend) | Analysis of project | 8 | 2016-02-08 | 2016-02-08 | AS | 0 | TO DO
6 | Chat Application | Mobile App(Frontend) | Estimate the project | 8 | 2016-02-05 | 2016-02-05 | MK | 100 | Done | Hold
|  |  | Analysis of pubnub api | 8 | 2016-02-06 | 2016-02-06 | MK | 0 | TO DO | Hold
7 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-08 | AM | 40 | WIP | Feature listing
MOM 09-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Writing a service for Timeline briefing page(timesheet) | 4 | 2016-01-05 | 2016-01-09 | ASC | 90 | WIP | Related to below one
|  |  | Implement the timesheet service on frontEnd Taiga | 8 | 2016-02-08 | 2016-02-09 | ASC | 50 | WIP | Implement and resolving the updation issue in Timesheet listing page for changes that is done on particular timesheet
2 | EmPerks | Mobile App(Frontend) | Add event in calender for reward | 4 | 2016-01-04 | 2016-01-08 | NP | 100 | Done | 8 Points on trello and working on 3 points
|  |  | Password based Redemption | 8 | 2016-01-08 | 2016-01-09 | NP | 0 | TO DO
|  |  | Reset Password | 1 | 2016-01-08 | 2016-01-08 | NP | 100 | Done
3 | My Street | Mobile App/WEB(Frontend) | Resolve 1 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | Hold | Apply validation on live deal pending from SJ side
4 | Parent Blocked | Mobile App(Frontend) | Analysis of project | 8 | 2016-02-08 | 2016-02-08 | AS | 100 | Done
6 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-08 | AM | 80 | Hold
7 | C P Jobsite | Mobile App(Frontend) | Analysis | 4 | 2016-02-09 | 2016-02-09 | AS | 0 | TO DO
8 | Learning | Mobile/Web | AngularJs 2 | 8 | 2016-02-02 | 2016-02-02 | NP | 20 | Hold
|  |  | Node Js(Node Blog system tut – 01) | 16 | 2016-02-09 | 2016-02-10 | AM | 0 | TO DO
MOM 10-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Writing a service for Timeline briefing page(timesheet) | 4 | 2016-01-05 | 2016-01-09 | ASC | 100 | Done
|  |  | Implement the timesheet service on frontEnd Taiga | 8 | 2016-02-08 | 2016-02-10 | ASC | 70 | WIP | updation is done(Resolving the redundency for same timesheet detail in timesheet briefing) ... feedback from SJ
2 | EmPerks | Mobile App(Frontend) | Password based Redemption | 8 | 2016-01-08 | 2016-01-09 | NP | 100 | Done | Stated by candidate
|  |  | Reset Password | 1 | 2016-01-08 | 2016-01-08 | NP | 100 | Done
|  |  | Add event in calender for DBSchenker and Ascott | 8 | 2016-02-10 | 2016-02-10 | NP | 0 | TO DO | As per client screen
3 | My Street | Mobile App/WEB(Frontend) | Resolve 1 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | Hold | Apply validation on live deal pending from SJ side
4 | Parent Blocked | Mobile App(Frontend) | Analysis of project | 8 | 2016-02-08 | 2016-02-08 | AS | 100 | Done
|  |  | Code Analysis | 8 | 2016-02-10 | 2016-02-10 | AS | 0 | TO DO
5 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-08 | AM | 80 | Hold
6 | Learning | Mobile/Web | AngularJs 2 | 8 | 2016-02-02 | 2016-02-02 | NP | 20 | Hold
|  |  | Node Js(Node Blog system tut – 01) | 16 | 2016-02-09 | 2016-02-10 | AM | 30 | WIP
MOM 11-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the timesheet service on frontEnd Taiga | 8 | 2016-02-08 | 2016-02-10 | ASC | 100 | Done | Completed for particular user not for manager
|  |  | Apply the Manger permission on Tiemsheet | 8 | 2016-02-11 | 2016-02-11 | ASC | 0 | WIP
2 | EmPerks | Mobile App(Frontend) | Add event in calender for DBSchenker and Ascott | 8 | 2016-02-10 | 2016-02-10 | NP | 100 | Done | As per client screen
|  |  | Routing and sevices in Angular2 | 8 | 2016-02-11 | 2016-02-11 | NP | 0 | WIP
3 | My Street | Mobile App/WEB(Frontend) | Resolve 1 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | Hold | Apply validation on live deal pending from SJ side
4 | Parent Blocked | Mobile App(Frontend) | Code Analysis | 8 | 2016-02-10 | 2016-02-10 | AS | 0 | TO DO | HOLD
5 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-08 | AM | 80 | Hold
6 | Learning | Mobile/Web | AngularJs 2 | 8 | 2016-02-02 | 2016-02-02 | NP | 20 | Hold
|  |  | Node Js(Node Blog system tut – 01) | 16 | 2016-02-09 | 2016-02-11 | AM | 30 | WIP
|  |  | JQuery Mobile design , Page transition list and Page event , Page transition | 8 | 2016-02-12 | 2016-02-12 | AS | 0 | WIP
MOM 12-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Apply the Manger permission on Tiemsheet | 8+4 | 2016-02-11 | 2016-02-12 | ASC | 40 | WIP
2 | EmPerks | Mobile App(Frontend) | Routing and sevices in Angular2 | 8 | 2016-02-11 | 2016-02-11 | NP | 0 | WIP | Absent
3 | My Street | Mobile App/WEB(Frontend) | Resolve 1 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | Hold | Apply validation on live deal pending from SJ side
4 | Parent Blocked | Mobile App(Frontend) | Code Analysis | 8 | 2016-02-10 | 2016-02-10 | AS | 0 | Hold
5 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-08 | AM | 80 | Hold
6 | Learning | Mobile/Web | AngularJs 2 | 8 | 2016-02-02 | 2016-02-02 | NP | 20 | Hold
|  |  | Node Js(Node Blog system tut – 01) | 16 | 2016-02-09 | 2016-02-11 | AM | 100 | Done
|  |  | JQuery Mobile design , Page transition list and Page event , Page transition | 8+4 | 2016-02-12 | 2016-02-12 | AS | 80 | Done | Page event is remaining and data transition between screens
|  |  | Node Js(Community Events –tut-06) | 4 | 2016-02-12 | 2016-02-12 | AM | 0 | TO DO
MOM 15-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Apply the Manger permission on Tiemsheet | 7 | 2016-02-11 | 2016-02-15 | ASC | 50 | WIP
2 | EmPerks | Mobile App(Frontend) | Routing and sevices in Angular2 | 8 | 2016-02-11 | 2016-02-11 | NP | 0 | WIP | Absent
3 | My Street | Mobile App/WEB(Frontend) | Resolve 1 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | Hold | Apply validation on live deal pending from SJ side
4 | Parent Blocked | Mobile App(Frontend) | Code Analysis | 8 | 2016-02-10 | 2016-02-10 | AS | 0 | Hold
5 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-08 | AM | 80 | Hold
6 | Learning | Mobile/Web | AngularJs 2(Navigation between two pages) | 8 | 2016-02-15 | 2016-02-15 | NP | 0 | TO DO
|  |  | JQuery Mobile design , Page transition list and Page event , Page transition | 8+4 | 2016-02-12 | 2016-02-12 | AS | 100 | Done | Page event is remaining and data transition between screens
|  |  | Node Js(Community Events –tut-06) | 4 | 2016-02-12 | 2016-02-15 | AM | 50 | WIP
|  |  | ToDo App in Jquery Mobile App | 8 | 2016-02-15 | 407657 | AS | 0 | WIP
MOM 16-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Apply the Manger permission on Tiemsheet | 8 | 2016-02-11 | 2016-02-16 | ASC | 50 | WIP | Having problem in filtering the timesheet briefing data related to user or manager
2 | My Street | Mobile App/WEB(Frontend) | Resolve 1 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | Hold | Apply validation on live deal pending from SJ side
3 | Parent Blocked | Mobile App(Frontend) | Code Analysis | 8 | 2016-02-10 | 2016-02-10 | AS | 0 | Hold
4 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-08 | AM | 80 | Hold
5 | Learning | Mobile/Web | AngularJs 2(Navigation between two pages) | 8 | 2016-02-15 | 2016-02-16 | NP | 0 | WIP
|  |  | Node Js(Community Events –tut-06) | 4 | 2016-02-12 | 2016-02-15 | AM | 100 | Done
|  |  | ToDo App in Jquery Mobile App | 8 | 2016-02-15 | 407658 | AS | 30 | Hold
|  |  | Mobile chat analysis ans estimation | 8 | 2016-02-16 | 2016-02-16 | AS | 0 | TO DO
MOM 17-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Apply the Manger permission on Tiemsheet | 8 | 2016-02-11 | 2016-02-16 | ASC | 100 | Done
|  |  | Testing and Backend Date range issue resolve | 7 | 2016-02-17 | 2016-02-17 | ASC | 0 | TO DO
2 | My Street | Mobile App/WEB(Frontend) | Resolve 1 points in Mail | 4 | 2016-01-22 | 2016-01-29 | AM | 90 | Hold | Apply validation on live deal pending from SJ side
3 | Parent Blocked | Mobile App(Frontend) | Code Analysis | 8 | 2016-02-10 | 2016-02-10 | AS | 0 | Hold
4 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-08 | AM | 80 | Hold
5 | Learning | Mobile/Web | AngularJs 2(Navigation between two pages) | 8 | 2016-02-15 | 2016-02-17 | NP | 0 | WIP
|  |  | ToDo App in Jquery Mobile App | 8 | 2016-02-15 | 407658 | AS | 30 | Hold
|  |  | Node Js(Book Store – tut - 01) | 8 | 2016-02-16 | 2016-02-16 | AM | 100 | Done
|  |  | Node Js(Chat IO – tut – 01) | 8 | 2016-02-17 | 2016-02-17 | AM | 0 | WIP
|  |  | Demo of pubnub chat app | 8 | 2016-02-16 | 2016-02-16 | AS | 100 | Done
6 | Chat App | Mobile App(Frontend) | Mobile chat analysis of pubnub and estimation | 8 | 2016-02-17 | 2016-02-17 | MK | 0 | TO DO
|  |  | pubnub analysis | 8 | 2016-02-17 | 2016-02-17 | AS | 0 | TO DO
MOM 18-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Apply the Manager permission on Tiemsheet | 8 | 2016-02-11 | 2016-02-16 | ASC | 100 | Done
|  |  | Testing and Backend Date range issue resolve | 7 | 2016-02-17 | 2016-02-18 | ASC | 50 | WIP | After testing feedback by AM resolve issue by ASC / resolving date range issue
2 | My Street | Mobile App/WEB(Frontend) | Resolve 8 points in Mail | 4 | 2016-02-18 | 2016-02-18 | AM | 0 | TO DO
3 | Parent Blocked | Mobile App(Frontend) | Code Analysis | 8 | 2016-02-10 | 2016-02-10 | AS | 0 | Hold
4 | FRID | Mobile App(Frontend) | Analysis and estimation | 14 | 2015-02-05 | 2016-02-08 | AM | 80 | Hold
5 | Learning | Mobile/Web | AngularJs 2(Navigation between two pages) | 8 | 2016-02-15 | 2016-02-17 | NP | 0 | Hold | Lack of Documentation
|  |  | ToDo App in Jquery Mobile App | 8 | 2016-02-15 | 407658 | AS | 30 | Hold
|  |  | Node Js(Chat IO – tut – 01) | 8 | 2016-02-17 | 2016-02-17 | AM | 100 | Done
6 | Chat App | Mobile App(Frontend) | Mobile chat analysis of pubnub and estimation | 8 | 2016-02-17 | 2016-02-17 | MK | 0 | TO DO
|  |  | pubnub analysis | 8 | 2016-02-17 | 2016-02-17 | AS | 100 | Done
7 | EmPerks | Mobile App(Frontend) | Local database add and remove event in calender | 8 | 2016-02-18 | 2016-02-18 | NP | 0 | TO DO
8 | C P Jobsite | Mobile App(Frontend) | Analysis and Project setup | 8 | 2015-02-18 | 2016-02-18 | AS | 0 | TO DO
MOM 19-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Testing and Backend Date range issue resolve | 7 | 2016-02-17 | 2016-02-18 | ASC | 100 | Done
|  |  | Implement the reject and reasons for that functionality in timesheet | 6 | 2016-02-19 | 2016-02-19 | ASC | 0 | TO DO
|  |  | Resolve some design issues in timesheet | 2 | 2016-02-19 | 2016-02-19 | ASC | 0 | TO DO
2 | My Street | Mobile App/WEB(Frontend) | Resolve 8 points in Mail | 4 | 2016-02-18 | 2016-02-19 | AM | 90 | WIP | 7 Points have been done
3 | Parent Blocked | Mobile App(Frontend) | Code Analysis | 8 | 2016-02-10 | 2016-02-10 | AS | 0 | Hold
4 | Learning | Mobile/Web | AngularJs 2(Navigation between two pages) | 8 | 2016-02-15 | 2016-02-17 | NP | 0 | Hold | Lack of Documentation
|  |  | ToDo App in Jquery Mobile App | 8 | 2016-02-15 | 407658 | AS | 30 | Hold
5 | Chat App | Mobile App(Frontend) | pubnub analysis | 8 | 2016-02-17 | 2016-02-17 | MK/AS | 100 | Done
|  |  | Implement notification functionality | 8 | 2016-02-19 | 2016-02-19 | MK | 0 | TO DO
6 | EmPerks | Mobile App(Frontend) | Local database add and remove event in calender | 8 | 2016-02-18 | 2016-02-19 | NP | 50 | WIP
7 | C P Jobsite | Mobile App(Frontend) | Analysis and Project setup | 8 | 2016-02-18 | 2016-02-19 | AS | 40 | WIP
MOM 20-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Testing and Backend Date range issue resolve | 7 | 2016-02-17 | 2016-02-18 | ASC | 100 | Done
|  |  | Implement the reject and reasons for that functionality in timesheet | 6 | 2016-02-19 | 2016-02-20 | ASC | 70 | WIP
|  |  | Resolve some design issues in timesheet | 2 | 2016-02-19 | 2016-02-19 | ASC | 100 | Done
2 | My Street | Mobile App/WEB(Frontend) | Resolve 8 points in Mail | 4 | 2016-02-18 | 2016-02-19 | AM | 100 | Done
3 | Parent Blocked | Mobile App(Frontend) | Code Analysis | 8 | 2016-02-10 | 2016-02-10 | AS | 0 | Hold
4 | Learning | Mobile/Web | AngularJs 2(Navigation between two pages) | 8 | 2016-02-15 | 2016-02-17 | NP | 0 | Hold | Lack of Documentation
|  |  | ToDo App in Jquery Mobile App | 8 | 2016-02-15 | 407658 | AS | 30 | Hold
5 | Chat App | Mobile App(Frontend) | pubnub analysis | 8 | 2016-02-17 | 2016-02-17 | MK/AS | 100 | Done
|  |  | Implement notification functionality | 8 | 2016-02-19 | 2016-02-19 | MK | 20 | WIP
6 | EmPerks | Mobile App(Frontend) | Local database add and remove event in calender | 8 | 2016-02-18 | 2016-02-20 | NP | 100 | WIP | Complete for ascott,remaining for other
|  |  | Local database add and remove event in calender | 8 | 2016-02-18 | 2016-02-20 | NP | 0 | TO DO
7 | C P Jobsite | Mobile App(Frontend) | Analysis and Project setup | 8 | 2016-02-18 | 2016-02-19 | AS | 100 | Done
|  |  | CP Jobsite estimation and analysis | 8 | 2016-02-20 | 2016-02-20 | AS/AM | 0 | TO DO
8 | EarnUp | Mobile App(Frontend) | Project Setup | 8 | 2016-02-20 | 2016-02-20 | AM | 0 | TO DO
MOM 22-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the reject and reasons for that functionality in timesheet | 6 | 2016-02-19 | 2016-02-22 | ASC | 80 | WIP | after completion feedback from sj
2 | My Street | Mobile App/WEB(Frontend) | Resolve 8 points in Mail | 4 | 2016-02-18 | 2016-02-22 | AM | 80 | WIP | 4 Points from sj side
3 | Chat App | Mobile App(Frontend) | Implement notification functionality | 8 | 2016-02-19 | 2016-02-22 | MK | 20 | WIP
4 | EmPerks | Mobile App(Frontend) | Local database add and remove event in calender | 8 | 2016-02-18 | 2016-02-20 | NP | 100 | WIP | Complete for ascott,remaining for other
|  |  | Local database add and remove event in calender | 4 | 2016-02-18 | 2016-02-22 | NP | 50 | WIP | Rewards and ignite remaing
|  |  | Trello 1 point | 4 | 2016-02-22 | 2016-02-22 | NP | 0 | TO DO
7 | C P Jobsite | Mobile App(Frontend) | Analysis and Project setup | 8 | 2016-02-18 | 2016-02-19 | AS | 100 | Done
|  |  | CP Jobsite estimation and analysis | 8 | 2016-02-20 | 2016-02-22 | AS/AM | 50 | WIP
8 | EarnUp | Mobile App(Frontend) | Project Setup | 8 | 2016-02-20 | 2016-02-22 | AM | 0 | WIP
MOM 23-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the reject and reasons for that functionality in timesheet | 7 | 2016-02-19 | 2016-02-23 | ASC | 90 | WIP | Unit Testing and resolve issue if any and Feedback from sj
2 | My Street | Mobile App/WEB(Frontend) | Resolve 8 points in Mail | 4 | 2016-02-18 | 2016-02-22 | AM | 80 | HOLD | 4 Points from sj side
3 | Chat App | Mobile App(Frontend) | Implement notification functionality | 8 | 2016-02-19 | 2016-02-23 | MK | 30 | WIP
4 | EmPerks | Mobile App(Frontend) | Local database add and remove event in calender | 8 | 2016-02-18 | 2016-02-20 | NP | 100 | WIP | Complete for ascott,remaining for other
|  |  | Local database add and remove event in calender | 4 | 2016-02-18 | 2016-02-22 | NP | 100 | Done | Rewards and ignite remaing
|  |  | Trello 1 point | 4 | 2016-02-22 | 2016-02-22 | NP | 100 | Done
5 | EarnUp | Mobile App(Frontend) | Project Setup | 8 | 2016-02-20 | 2016-02-22 | AM | 100 | Done
|  |  | analysis of earnup analysis | 8 | 2016-02-23 | 2016-02-23 | AS | 0 | WIP
6 | Learning | Node js | Vedio tutorial – 8 | 8 | 2016-02-23 | 2016-02-23 | AM | 0 | TO DO
|  | Custom url scheme | Phone gap plugin for open other app | 8 | 2016-02-23 | 2016-02-23 | NP | 0 | TO DO
MOM 24-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the reject and reasons for that functionality in timesheet | 7 | 2016-02-19 | 2016-02-23 | ASC | 100 | WIP
|  |  | Change the format of date picker , hide the submit button for no data and small refinement points | 7 | 2016-02-24 | 2016-02-24 | ASC | 0 | TODO
2 | My Street | Mobile App/WEB(Frontend) | Resolve 8 points in Mail | 4 | 2016-02-18 | 2016-02-22 | AM | 80 | HOLD | 4 Points from sj side
3 | Chat App | Mobile App(Frontend) | Implement notification functionality | 8 | 2016-02-19 | 2016-02-24 | MK | 30 | WIP
4 | EmPerks | Mobile App(Frontend) | Password based Redemption | 4 | 2016-02-23 | 2016-02-23 | NP | 100 | Done
|  |  | Unit Testing | 4 | 2016-02-24 | 2016-02-24 | NP | 0 | TO DO
5 | EarnUp | Mobile App(Frontend) | analysis of earnup analysis | 8 | 2016-02-23 | 2016-02-24 | AS | 30 | WIP | Resolving 3 points put of 6 points
6 | Learning | Node js | Vedio tutorial – 8 | 8 | 2016-02-23 | 2016-02-23 | AM | 0 | HOLD
|  | Custom url scheme | Phone gap plugin for open other app | 4 | 2016-02-23 | 2016-02-24 | NP | 0 | WIP
MOM 25-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the reject and reasons for that functionality in timesheet | 7 | 2016-02-19 | 2016-02-23 | ASC | 100 | WIP
|  |  | Change the format of date picker , hide the submit button for no data and small refinement points | 7 | 2016-02-24 | 2016-02-25 | ASC | 80 | WIP | Resolve the design issue related with datpicker and testing
2 | My Street | Mobile App/WEB(Frontend) | Resolve points | 1 | 2016-02-25 | 2016-02-25 | NP | 0 | TO DO
3 | Chat App | Mobile App(Frontend) | Implement notification functionality | 8 | 2016-02-19 | 2016-02-25 | MK | 40 | WIP
4 | EmPerks | Mobile App(Frontend) | Password based Redemption | 4 | 2016-02-23 | 2016-02-23 | NP | 100 | Done
|  |  | Unit Testing | 4 | 2016-02-24 | 2016-02-25 | NP | 0 | WIP
|  |  | Refinement Points | 8 | 2016-02-24 | 2016-02-24 | NP | 100 | Done
5 | Learning | Node js | Vedio tutorial – 8 | 8 | 2016-02-23 | 2016-02-23 | AM | 0 | HOLD
|  | Custom url scheme | Phone gap plugin for open other app | 3 | 2016-02-23 | 2016-02-25 | NP | 0 | WIP
6 | CP Job Site | Mobile App(Frontend) | News feed analysis | 8 | 2016-02-25 | 2016-02-25 | AS | 0 | TO DO
MOM 26-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Change the format of date picker , hide the submit button for no data and small refinement points | 7 | 2016-02-24 | 2016-02-25 | ASC | 90 | WIP
|  |  | Implement the date format on timesheet message page for existed timesheet remaining | 7 | 2016-02-25 | 2016-02-26 | ASC | 0 | TO DO
2 | My Street | Mobile App/WEB(Frontend) | Resolve points | 1 | 2016-02-25 | 2016-02-25 | NP | 100 | Done
3 | Chat App | Mobile App(Frontend) | Implement notification functionality | 8 | 2016-02-19 | 2016-02-25 | MK | 40 | WIP | Absent
4 | Learning | Node js | Vedio tutorial – 8 | 8 | 2016-02-23 | 2016-02-23 | AM | 0 | HOLD
|  | Custom url scheme | Phone gap plugin for open other app | 3 | 2016-02-23 | 2016-02-26 | NP | 0 | WIP
5 | CP Job Site | Mobile App(Frontend) | News feed analysis | 8 | 2016-02-25 | 2016-02-25 | AS | 80 | WIP
|  |  | Update Jobs update analysis | 8 | 2016-02-26 | 2016-02-26 | AS | 0 | TO DO
MOM 29-Feb-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Change the format of date picker , hide the submit button for no data and small refinement points | 7 | 2016-02-24 | 2016-02-25 | ASC | 90 | WIP | absent
|  |  | Implement the date format on timesheet message page for existed timesheet remaining | 7 | 2016-02-25 | 2016-02-26 | ASC | 0 | TO DO
2 | My Street | Mobile App/WEB(Frontend) | Resolve points | 1 | 2016-02-25 | 2016-02-25 | NP | 100 | Done
3 | Chat App | Mobile App(Frontend) | Implement notification functionality | 8 | 2016-02-19 | 2016-02-25 | MK | 40 | WIP
4 | Learning | Node js | Vedio tutorial – 8 | 8 | 2016-02-23 | 2016-02-23 | AM | 0 | HOLD
|  | Custom url scheme | Phone gap plugin for open other app | 3 | 2016-02-23 | 2016-02-26 | NP | 0 | WIP
5 | CP Job Site | Mobile App(Frontend) | News feed analysis | 8 | 2016-02-25 | 2016-02-25 | AS | 80 | WIP
|  |  | Update Jobs update analysis | 8 | 2016-02-26 | 2016-02-26 | AS | 50 | TO DO
MOM-01-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Change the format of date picker , hide the submit button for no data and small refinement points | 7 | 2016-02-24 | 2016-02-25 | ASC | 100 | Done
|  |  | Implement the date format on timesheet message page for existed timesheet remaining | 7 | 2016-02-25 | 2016-02-26 | ASC | 100 | Done
|  |  | Design of Project Bidding Module and Creating the modal for that on backend | 7.5 | 2016-02-29 | 2016-03-01 | ASC | 40 | WIP | Working on design of project bidding module and framing controller for that with local data today.
2 | Chat App | Mobile App(Frontend) | Plugin Integrate,GCM service integrated | 8 | 2016-02-19 | 2016-02-01 | MK | 100 | Done
|  |  | Implementation for push notification | 8 | 2016-03-01 | 2016-03-01 | MK | 0 | TO DO
3 | Learning | Node js | Vedio tutorial – 8 | 8 | 2016-02-23 | 2016-02-23 | AM | 0 | HOLD
|  | Custom url scheme | Phone gap plugin for open other app | 3 | 2016-02-23 | 2016-03-01 | NP | 0 | WIP | Indent Plugin integration
4 | CP Job Site | Mobile App(Frontend) | News feed analysis | 8 | 2016-02-25 | 2016-02-25 | AS | 100 | Done
|  |  | Update Jobs update analysis | 8 | 2016-02-26 | 2016-03-01 | AS | 70 | WIP
MOM-02-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Design of Project Bidding Module and Creating the modal for that on backend | 7.5 | 2016-02-29 | 2016-03-01 | ASC | 100 | Done
|  |  | Implement the service for bidding project module and consume it on frontend | 8 | 2016-03-02 | 2016-03-02 | ASC | 0 | WIP
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 8 | 2016-03-01 | 2016-03-02 | MK | 30 | WIP
3 | Learning | Node js | Vedio tutorial – 8 | 8 | 2016-02-23 | 2016-02-23 | AM | 0 | HOLD
|  | Custom url scheme | Phone gap plugin for open other app | 3 | 2016-02-23 | 2016-03-02 | NP | 0 | WIP
4 | CP Job Site | Mobile App(Frontend) | Update Jobs update analysis | 8 | 2016-02-26 | 2016-03-01 | AS | 100 | Done
|  |  | Add test module , List page and detail page | 8 | 2016-03-02 | 2016-03-02 | AS | 0 | WIP
5 | EmPerk | Mobile App(Frontend) | Password Redemption issue for ignite | 8 | 2016-03-01 | 2016-03-01 | NP | 100 | Done
MOM-03-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Design of Project Bidding Module and Creating the modal for that on backend | 7.5 | 2016-02-29 | 2016-03-01 | ASC | 100 | Done
|  |  | Implement the service for bidding project module and consume it on frontend | 8 | 2016-03-02 | 2016-03-03 | ASC | 80 | WIP | Unit Testing and resolving the issue if any and feedback from S J
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 8 | 2016-03-01 | 2016-03-03 | MK | 30 | WIP
3 | Learning | Node js | Vedio tutorial – 8 | 8 | 2016-02-23 | 2016-02-03 | AM | 0 | WIP
|  | Custom url scheme | Phone gap plugin for open other app | 3 | 2016-02-23 | 2016-03-03 | NP | 0 | WIP
4 | CP Job Site | Mobile App(Frontend) | Update Jobs update analysis | 8 | 2016-02-26 | 2016-03-01 | AS | 100 | Done
|  |  | Add test module , List page and detail page | 8 | 2016-03-02 | 2016-03-03 | AS | 30 | WIP | Work on detail page
5 | EmPerk | Mobile App(Frontend) | Trello Points | 8 | 2016-03-03 | 2016-03-03 | NP | 0 | WIP
MOM-04-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the service for bidding project module and consume it on frontend | 8 | 2016-03-02 | 2016-03-03 | ASC | 100 | WIP
|  |  | 8 new points in project bidding section | 7.5 | 2016-03-04 | 2016-03-04 | ASC | 0 | TO DO
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 8 | 2016-03-01 | 2016-03-04 | MK | 50 | WIP
3 | Learning | Node js | Vedio tutorial – 8 | 4 | 2016-02-23 | 2016-02-03 | AM | 50 | WIP
|  | Custom url scheme | Phone gap plugin for open other app | 4 | 2016-02-23 | 2016-03-04 | NP | 0 | WIP
4 | CP Job Site | Mobile App(Frontend) | Add test module , List page and detail page | 8 | 2016-03-02 | 2016-03-03 | AS | 100 | Done
|  |  | Push Notification | 8 | 2016-03-04 | 2016-03-04 | AS | 0 | TO DO
5 | EmPerk | Mobile App(Frontend) | Trello Points | 8 | 2016-03-03 | 2016-03-03 | NP | 100 | Done | Rewardz Redemption without location and password
|  |  | Term & Condition Bullet points | 4 | 2016-03-04 | 2016-03-04 | NP | 0 | WIP
6 | RootInfosol.com(Content Creation) | Content Creation | Node Js and php page | 8 | 2016-03-04 | 2016-03-04 | DG | 0 | TO DO
7 | MyStreet | Web Projects(Backend) | Generate PDF | 4 | 2016-03-04 | 2016-03-04 | AM | 0 | TO DO
MOM 05-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the service for bidding project module and consume it on frontend | 8 | 2016-03-02 | 2016-03-03 | ASC | 100 | WIP
|  |  | 8 new points in project bidding section | 7.5+8 | 2016-03-04 | 2016-03-05 | ASC | 60 | WIP | Remaining 3 Points --- Filter(continue),Log a note and pagination on frontend Desing done , filter by status and by user done by date range filtering remaining
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 4 | 2016-03-01 | 2016-03-05 | MK | 50 | WIP | Send push notification when app is in background is remaining
|  |  | Show Chat history | 4 | 2016-03-05 | 2016-03-05 | MK | 100 | Done | show chate history completed
3 | Learning | Node js | Vedio tutorial – 8 | 4 | 2016-02-23 | 2016-02-03 | AM | 100 | Done
|  | Custom url scheme | Phone gap plugin for open other app(Indent Plugin) | 8 | 2016-02-23 | 2016-03-05 | NP | 0 | WIP | Still pending because of native side . Learing of custome plugin in cordova is in progress
|  | Node js | Vedio tutorial – 9 | 8 | 2016-03-05 | 2016-03-05 | AM | 50 | WIP | Video completed but need to implement it
4 | CP Job Site | Mobile App(Frontend) | Add test module , List page and detail page | 8 | 2016-03-02 | 2016-03-03 | AS | 100 | Done | note done – getting issue -> Failed to load resource: the server responded with a status of 422 (Unprocessable Entity)
|  |  | Push Notification | 8 | 2016-03-04 | 2016-03-05 | AS | 0 | WIP
6 | MyStreet | Web Projects(Backend) | Generate PDF | 4 | 2016-03-04 | 2016-03-04 | AM | 100 | Done
MOM 07-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the service for bidding project module and consume it on frontend | 8 | 2016-03-02 | 2016-03-03 | ASC | 100 | WIP
|  |  | 8 new points in project bidding section | 7.5+8 | 2016-03-04 | 2016-03-05 | ASC | 100 | Done
|  |  | Filtering on the basis of date and log a note | 7.5 | 2016-03-07 | 2016-03-07 | ASC | 100 | Done
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 4 | 2016-03-01 | 2016-03-05 | MK | 50 | WIP | Send push notification when app is in background is remaining
|  |  | Show Chat history | 4 | 2016-03-05 | 2016-03-05 | MK | 100 | Done | show chate history completed
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-07 | MK | 30 | WIP | facebook integration is done and authontication of user is in progress
3 | Learning | Node js | Vedio tutorial – 8 | 4 | 2016-02-23 | 2016-02-03 | AM | 100 | Done
|  | Custom url scheme | Phone gap plugin for open other app(Indent Plugin) | 8 | 2016-02-23 | 2016-03-07 | NP | 40 | WIP | Open another app completed. Send token to another app is in progress
|  | Node js | Vedio tutorial – 9 | 4 | 2016-03-05 | 2016-03-07 | AM | 100 | WIP | Done
4 | CP Job Site | Mobile App(Frontend) | Add test module , List page and detail page | 8 | 2016-03-02 | 2016-03-03 | AS | 100 | Done
|  |  | Push Notification | 4 | 2016-03-04 | 2016-03-07 | AS | 60 | WIP | everything done but when making build does not get device connected on web portal. That is why unable to send notification. Replicating issue.
|  |  | test review and estimation | 4 | 2016-03-07 | 2016-03-07 | AS | 100 | Done
6 | MyStreet | Web Projects(Backend) | Resolve leave issue | 4 | 2016-03-07 | 2016-03-07 | AM | 0 | HOLD | Waiting for SJ response
MOM 08-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the service for bidding project module and consume it on frontend | 8 | 2016-03-02 | 2016-03-03 | ASC | 100 | WIP
|  |  | 8 new points in project bidding section | 7.5+8 | 2016-03-04 | 2016-03-05 | ASC | 100 | Done
|  |  | Filtering on the basis of date and log a note | 7.5 | 2016-03-07 | 2016-03-07 | ASC | 100 | Done
|  |  | Pagination and log a note extended functionality for attachments | 7.5 | 2016-03-08 | 2016-03-08 | ASC | 60 | WIP | getting error when submit log note with attachment
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 4 | 2016-03-01 | 2016-03-05 | MK | 50 | WIP | Send push notification when app is in background is remaining
|  |  | Show Chat history | 4 | 2016-03-05 | 2016-03-05 | MK | 100 | Done | show chate history completed
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-08 | MK | 30 | WIP | plugin is not supported app getting crashed when authorising
3 | Learning | Node js | Vedio tutorial – 8 | 4 | 2016-02-23 | 2016-02-03 | AM | 100 | Done
|  | Custom url scheme | Phone gap plugin for open other app(Indent Plugin) | 8 | 2016-02-23 | 2016-03-08 | NP | 40 | WIP | Send token in Indent plugin is still pending
|  | Node js | Vedio tutorial – 9 | 4 | 2016-03-05 | 2016-03-07 | AM | 100 | WIP | Done
|  |  | Vedio tutorial – 10 | 8 | 2016-03-08 | 2016-03-08 | AM | 60 | WIP | Portfolio app - 6 video watched out of 10
4 | CP Job Site | Mobile App(Frontend) | Add test module , List page and detail page | 8 | 2016-03-02 | 2016-03-03 | AS | 100 | Done
|  |  | Push Notification | 4 | 2016-03-04 | 2016-03-08 | AS | 100 | done
|  |  | test review and estimation | 4 | 2016-03-07 | 2016-03-07 | AS | 100 | Done
|  |  | facebook integration | 8 | 2016-03-08 | 2016-03-08 | AS | 0 | WIP
6 | MyStreet | Web Projects(Backend) | Resolve live issue | 4 | 2016-03-07 | 2016-03-08 | AM | 0 | HOLD | Waiting for SJ response
MOM 09-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Implement the service for bidding project module and consume it on frontend | 8 | 2016-03-02 | 2016-03-03 | ASC | 100 | WIP
|  |  | 8 new points in project bidding section | 7.5+8 | 2016-03-04 | 2016-03-05 | ASC | 100 | Done
|  |  | Filtering on the basis of date and log a note | 7.5 | 2016-03-07 | 2016-03-07 | ASC | 100 | Done
|  |  | Pagination and log a note extended functionality for attachments | 7.5 | 2016-03-08 | 2016-03-09 | ASC | 90 | WIP | Issue in attachment is resolved.
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 4 | 2016-03-01 | 2016-03-05 | MK | 50 | WIP | Send push notification when app is in background is remaining
|  |  | Show Chat history | 4 | 2016-03-05 | 2016-03-05 | MK | 100 | Done | show chate history completed
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-09 | MK | 50 | WIP | 1.install facebook plugin done 2. create account on facebook developers and create app there generate app_id done 3. install facebook SK done
3 | Learning | Node js | Vedio tutorial – 8 | 4 | 2016-02-23 | 2016-02-03 | AM | 100 | Done
|  | Custom url scheme | Phone gap plugin for open other app(Indent Plugin) | 8 | 2016-02-23 | 2016-03-09 | NP | 100 | Done | Next day task isl Implement intent plugin in rewardz and dbshanker
|  | Node js | Vedio tutorial – 9 | 4 | 2016-03-05 | 2016-03-07 | AM | 100 | Done
|  |  | Vedio tutorial – 10 | 4 | 2016-03-08 | 2016-03-09 | AM | 100 | Done
|  |  | Vedio tutorial – 11 | 4 | 2016-03-09 | 2016-03-09 | AM | 50 | WIP | 5 viedo out of 10 is watched
4 | CP Job Site | Mobile App(Frontend) | facebook integration | 8 | 2016-03-08 | 2016-03-09 | AS | 100 | Done | Facebook intgration completed
6 | MyStreet | Web Projects(Backend) | Resolve live issue | 4 | 2016-03-07 | 2016-03-08 | AM | 0 | HOLD | Waiting for SJ response
MOM 10-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Pagination and log a note extended functionality for attachments | 7.5 | 2016-03-08 | 2016-03-10 | ASC | 90 | WIP | resolving pagination issue in filtering
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 4 | 2016-03-01 | 2016-03-05 | MK | 50 | WIP | Send push notification when app is in background is remaining
|  |  | Show Chat history | 4 | 2016-03-05 | 2016-03-05 | MK | 100 | Done | show chate history completed
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-10 | MK | 50 | WIP | 1.install facebook plugin done 2. create account on facebook developers and create app there generate app_id done 3. install facebook SK done
3 | Learning | Node js | Vedio tutorial – 11 | 4 | 2016-03-09 | 2016-03-10 | AM | 50 | WIP | 5 viedo out of 10 is watched
|  |  | Integrate indent plugin in rewards and dbschenker | 8 | 2016-03-10 | 2016-03-10 | AM | 0 | TO DO
|  |  | Slider tutorial and Total Videos | 8 | 2016-03-10 | 2016-03-10 | AM | 0 | TO DO
4 | CP Job Site | Mobile App(Frontend) | facebook integration | 8 | 2016-03-08 | 2016-03-09 | AS | 100 | Done | Facebook intgration completed
|  |  | fb contact List and fb Profile Page | 8 | 2016-03-10 | 2016-03-10 | AS | 0 | TO DO
6 | MyStreet | Web Projects(Backend) | Resolve live issue | 4 | 2016-03-07 | 2016-03-08 | AM | 0 | HOLD | Waiting for SJ response
MOM 11-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Pagination and log a note extended functionality for attachments | 7.5 | 2016-03-08 | 2016-03-11 | ASC | 90 | WIP | resolving pagination issue in filtering ad file uploading
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 4 | 2016-03-01 | 2016-03-05 | MK | 50 | WIP | Send push notification when app is in background is remaining
|  |  | Show Chat history | 4 | 2016-03-05 | 2016-03-05 | MK | 100 | Done | show chate history completed
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-10 | MK | 50 | WIP | 1.install facebook plugin done 2. create account on facebook developers and create app there generate app_id done 3. install facebook SK done
3 | Learning | Node js | Vedio tutorial – 11 | 4 | 2016-03-09 | 2016-03-11 | AM | 50 | WIP | 5 viedo out of 10 is watched
|  |  | Integrate indent plugin in rewards and dbschenker | 8 | 2016-03-10 | 2016-03-10 | NP | 0 | TO DO
|  |  | Slider tutorial | 4 | 2016-03-10 | 2016-03-11 | AM | 30 | TO DO
4 | CP Job Site | Mobile App(Frontend) | fb contact List and fb Profile Page | 8 | 2016-03-10 | 2016-03-11 | AS | 0 | TO DO | getting error in hash key generation
5 | Emperk | Mobile App(Frontend) | Intent Plugin refinement | 8 | 2016-03-11 | 2016-03-11 | NP | 0 | TO DO | Event is not working when another app is open
6 | MyStreet | Web Projects(Backend) | Resolve live issue | 4 | 2016-03-07 | 2016-03-08 | AM | 0 | HOLD | Waiting for SJ response
MOM 14-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Pagination and log a note extended functionality for attachments. | 7.5 | 2016-03-08 | 2016-03-14 | ASC | 100 | Done | Attachment is excluded.will be implemented later.testing and resolved 20 bugs
2 | Chat App | Mobile App(Frontend) | Implementation for push notification | 4 | 2016-03-01 | 2016-03-05 | MK | 50 | Hold | Send push notification when app is in background is remaining
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-14 | MK | 90 | WIP | fetch fb friend list and integrate it for live chat but getting error in ser recognition.
3 | Learning | Node js | Vedio tutorial – 11 | 4 | 2016-03-09 | 2016-03-11 | AM | 50 | WIP | 5 video out of 10 is watched
|  |  | Slider tutorial | 4 | 2016-03-10 | 2016-03-14 | AM | 95 | Done | Task completed , refinement and smoothness will done if required
4 | CP Job Site | Mobile App(Frontend) | fb contact List and fb Profile Page | 8 | 2016-03-10 | 2016-03-14 | AS | 80 | WIP | Fb profile page done, fb contact list fetched only need to show on screens.
5 | Emperk | Mobile App(Frontend) | Intent Plugin refinement (Implement intent plugin in Reward and Dbshenker .) | 8 | 2016-03-11 | 2016-03-14 | NP | 95 | WIP | On resume app open issue is remaing.
6 | MyStreet | Web Projects(Backend) | Resolve live issue | 4 | 2016-03-07 | 2016-03-08 | AM | 0 | HOLD | Waiting for SJ response
MOM 15-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | Pagination and log a note extended functionality for attachments. | 7.5 | 2016-03-08 | 2016-03-14 | ASC | 100 | Done | Attachment is excluded.will be implemented later.testing and resolved 20 bugs
|  |  | testing and bug fixes | 6 | 2016-03-15 | 2016-03-15 | ASC | 0 | TO DO | Does not have status update
2 | Chat App | Mobile App(Frontend) | Implementation for push notification -cold start | 4 | 2016-03-01 | 2016-03-05 | MK | 50 | WIP | After finishing “live chat user” will resolve issue of this task and integrate it into app
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-14 | MK | 90 | WIP | Still not finished
3 | Learning | Node js | Vedio tutorial – 11 | 4 | 2016-03-09 | 2016-03-11 | AM | 100 | Done
|  |  | file upload | 2 | 2016-03-15 | 2016-03-15 | ASC |  | TO DO | Does not have status update
|  |  | Slider tutorial | 4 | 2016-03-10 | 2016-03-14 | AM | 95 | Done | Smoothness is remaing
4 | CP Job Site | Mobile App(Frontend) | fb contact List and fb Profile Page | 8 | 2016-03-10 | 2016-03-15 | AS | 100 | Done
5 | Emperk | Mobile App(Frontend) | Intent Plugin refinement (Implement intent plugin in Reward and Dbshenker .) | 8 | 2016-03-11 | 2016-03-14 | NP | 100 | Done
|  |  | 4 points on trello | 4 | 2016-03-15 | 2016-03-15 | NP | 100 | Done
6 | MyStreet | Web Projects(Backend) | Resolve live issue | 4 | 2016-03-07 | 2016-03-08 | AM | 0 | HOLD | Waiting for SJ response
MOM 16-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | testing and bug fixes | 6 | 2016-03-15 | 2016-03-15 | ASC | 80 | WIP | Total 31 issues 25 resolved 6 need to resolve. Today raised 9 issue 5 is resolved 4 remaining
|  |  | making production server for testing | 2 | 2016-03-16 | 2016-03-16 | ASC | 100 | done
2 | Chat App | Mobile App(Frontend) | Implementation for push notification -cold start | 4 | 2016-03-01 | 2016-03-15 | MK | 50 | WIP | After finishing “live chat user” will resolve issue of this task and integrate it into app
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-14 | MK | 90 | WIP | chat between facebook friends (one to one chat, or group chat ) in-process
3 | Learning | Node js | Vedio tutorial – 11 | 4 | 2016-03-09 | 2016-03-11 | AM | 100 | Done
|  |  | file upload | 2 | 2016-03-15 | 2016-03-15 | ASC | 10 | WIP | projects setup done need to implement
|  |  | Slider tutorial | 4 | 2016-03-10 | 2016-03-14 | AM | 95 | Done | Smoothness is remaing
4 | CP Job Site | Mobile App(Frontend) | fb contact List and fb Profile Page | 8 | 2016-03-10 | 2016-03-15 | AS | 100 | Done
|  |  | Google+ integration | 8 | 2016-03-16 | 2016-03-16 | AS | 100 | Done
5 | Emperk | Mobile App(Frontend) | Trello 3 points | 4 | 2006-03-16 | 2006-03-16 | NP | 100 | Done | Project setup done development also done 25%;
Cossb projects setup
6 | MyStreet | Web Projects(Backend) | Resolve live issue + 5 issues | 4 | 2016-03-07 | 2016-03-16 | AM | 80 | WIP | All issue resolved excep live issue and fb connection issue on backend side
MOM 17-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | testing and bug fixes | 6 + 8 | 2016-03-15 | 2016-03-17 | ASC | 80 | WIP | ISSUE:- 44, SOVELD:- 40,PENDING :- 4
|  |  | making production server for testing | 2 | 2016-03-16 | 2016-03-16 | ASC | 100 | done
2 | Chat App | Mobile App(Frontend) | Implementation for push notification -cold start | 4 | 2016-03-01 | 2016-03-15 | MK | 50 | WIP | After finishing “live chat user” will resolve issue of this task and integrate it into app
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-14 | MK | 90 | WIP | one to one chat creating problem that he is unable to create private channel for every chat user
3 | Learning | Node js | Node Js Tutorian 11 implementaion | 8 | 2016-03-17 | 2016-03-17 |  | 0 | TO DO | Still not started
|  |  | file upload | 2 | 2016-03-15 | 2016-03-15 | ASC | 10 | Hold
|  |  | Slider tutorial | 4 | 2016-03-10 | 2016-03-14 | AM | 95 | Done | Smoothness is remaing
4 | CP Job Site | Mobile App(Frontend) | fb contact List and fb Profile Page | 8 | 2016-03-10 | 2016-03-15 | AS | 100 | Done
|  |  | Google+ integration | 8 | 2016-03-16 | 2016-03-16 | AS | 100 | Done
|  |  | Twitter Integration | 8 | 2016-03-17 | 2016-03-17 | AS | 0 | WIP | Unknown provider: $cordovaOauthProvider <- $cordovaOauth
5 | Emperk | Mobile App(Frontend) | Trello 3 points | 4 | 2006-03-16 | 2006-03-16 | NP | 100 | Done
|  |  | Cossb projects setup and development | 4 | 2016-03-16 | 2016-03-16 | NP | 90 | WIP | Refinement is remaining
6 | MyStreet | Web Projects(Backend) | Resolve live issue + 5 issues | 4 | 2016-03-07 | 2016-03-16 | AM | 90 | WIP | All issue resolved except live issue
MOM 18-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | testing and bug fixes | 6 + 8 | 2016-03-15 | 2016-03-18 | ASC | 100 | Done | Resolved
|  |  | making production server for testing | 2 | 2016-03-16 | 2016-03-16 | ASC | 100 | done
2 | Chat App | Mobile App(Frontend) | Implementation for push notification -cold start | 4 | 2016-03-01 | 2016-03-15 | MK | 50 | WIP | After finishing “live chat user” will resolve issue of this task and integrate it into app
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-18 | MK | 90 | WIP | Still problem is not resolved
3 | Learning | Node js | Node Js Tutorian 11 implementaion | 8 | 2016-03-17 | 2016-03-17 |  | 0 | Hold
|  |  | file upload | 2 | 2016-03-15 | 2016-03-15 | ASC | 10 | Hold
|  |  | Slider implementation | 4 | 2016-03-10 | 2016-03-14 | AM | 30 | WIP | Need to implement it by new approach
4 | CP Job Site | Mobile App(Frontend) | fb contact List and fb Profile Page | 8 | 2016-03-10 | 2016-03-15 | AS | 100 | Done
|  |  | Google+ integration | 8 | 2016-03-16 | 2016-03-16 | AS | 100 | Done
|  |  | Twitter Integration | 8 | 2016-03-17 | 2016-03-18 | AS | 100 | Done
5 | Emperk | Mobile App(Frontend) | Trello 4 points | 4 | 2006-03-16 | 2006-03-18 | NP | 0 | Hold | Need to dscuss (doing project estimation)
|  |  | Cossb projects setup and development | 4 | 2016-03-16 | 2016-03-18 | NP | 90 | Hold | Refinement is remaining (doing project estimation)
6 | MyStreet | Web Projects(Backend) | Resolve live issue + 5 issues | 4 | 2016-03-07 | 2016-03-16 | AM | 90 | WIP | All issue resolved except live issue
7 | Companion | Project Estimation | Project Estimation | 4 | 2016-03-18 | 2016-03-18 | NP | 100 | Done | attachment forwarded
MOM 19-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | testing and bug fixes | 6 + 8 | 2016-03-15 | 2016-03-18 | ASC | 100 | Done | Resolved
|  |  | making production server for testing | 2 | 2016-03-16 | 2016-03-16 | ASC | 100 | done | Need to be pushed code
2 | Chat App | Mobile App(Frontend) | Implementation for push notification -cold start | 4 | 2016-03-01 | 2016-03-15 | MK | 50 | WIP | After finishing “live chat user” will resolve issue of this task and integrate it into app
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-19 | MK | 90 | WIP | able to send message through private chanel but unable to recieve and mentain session between two users
3 | Learning | Node js | Node Js Tutorian 11 implementaion | 8 | 2016-03-17 | 2016-03-17 |  | 0 | Hold
|  |  | file upload | 2 + 4 | 2016-03-15 | 2017-03-19 | ASC | 10 | WIP
|  |  | Slider implementation | 4 + 8 | 2016-03-10 | 2016-03-19 | AM | 30 | WIP | Today it must be finished
4 | CP Job Site | Mobile App(Frontend) | fb contact List and fb Profile Page | 8 | 2016-03-10 | 2016-03-15 | AS | 100 | Done
|  |  | Google+ integration | 8 | 2016-03-16 | 2016-03-16 | AS | 100 | Done
|  |  | Twitter Integration | 8 | 2016-03-17 | 2016-03-18 | AS | 100 | Done
5 | Emperk | Mobile App(Frontend) | Trello 4 points | 4 | 2006-03-16 | 2006-03-18 | NP | 0 | Hold | Need to dscuss (doing project estimation)
|  |  | Cossb projects setup and development | 4 | 2016-03-16 | 2016-03-18 | NP | 90 | WIP | Refinement is remaining (doing project estimation)
6 | MyStreet | Web Projects(Backend) | Resolve live issue + 5 issues | 4 | 2016-03-07 | 2016-03-16 | AM | 90 | WIP | All issue resolved except live issue
7 | Companion | Project Estimation | Project Estimation | 4 | 2016-03-18 | 2016-03-18 | NP | 100 | Done | attachment forwarded
MOM 21-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | making production server for testing | 2 | 2016-03-16 | 2016-03-16 | ASC | 100 | Done | Need to be pushed code
2 | Chat App | Mobile App(Frontend) | Implementation for push notification -cold start | 4 | 2016-03-01 | 2016-03-15 | MK | 50 | WIP | After finishing “live chat user” will resolve issue of this task and integrate it into app
|  |  | Show Live chat User & Cold start | 8 | 2016-03-07 | 2016-03-21 | MK | 90 | WIP | able to send message through private chanel but unable to recieve and mentain session between two users
3 | Learning | Node js | Node Js Tutorian 11 implementaion | 8 | 2016-03-17 | 2016-03-17 |  | 0 | Hold
|  |  | file upload | 4 + 8 | 2016-03-19 | 2016-03-21 | ASC | 40 | WIP | Further task will be assigned by SJ .
|  |  | Slider implementation and integration | 4 + 8 + 8 | 2016-03-10 | 2016-03-21 | AM | 50 | WIP | Today it must be finished (Complete from AM side need to integrate it in live side)
4 | CP Job Site | Mobile App(Frontend) | Twitter Integration | 8 | 2016-03-17 | 2016-03-18 | AS | 100 | Done
|  |  | Project setup and login page design in ionic framework | 8 | 2016-03-21 | 2016-03-21 | AS | 0 | TO DO
5 | Emperk | Mobile App(Frontend) | Trello 4 points | 4 | 2006-03-16 | 2006-03-18 | NP | 0 | Hold | Need to dscuss (doing project estimation)
|  |  | Cossb projects setup and development | 4 | 2016-03-16 | 2016-03-18 | NP | 90 | Hold | Refinement is remaining (doing project estimation)
6 | MyStreet | Web Projects(Backend) | Resolve live issue + 5 issues | 4 | 2016-03-07 | 2016-03-16 | AM | 90 | Hold | All issue resolved except live issue
7 | Companion | Project Estimation | Project Estimation | 4 | 2016-03-18 | 2016-03-18 | NP | 100 | Done | attachment forwarded
MOM 28-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | feedback from sj and new task assignment from sj |  | 2016-03-28 | 2016-03-28 | ASC | 0 | TO DO | Currently working on basic demo for file upload
2 | Chat App | Mobile App(Frontend) | Push Integration (Cold Start) | 8 | 2016-03-28 | 2016-03-28 | MK | 50 | WIP
3 | Learning | Node js | Make a rest api for upload file | 8 | 2016-03-28 | 2016-03-28 | AM | 0 | TO DO
4 | CP Job Site | Mobile App(Frontend) | News feed list page | 8 | 2016-03-28 | 2016-03-28 | AS | 0 | TO DO

## H P
S . no | Project | Comment
1 | Easy Futbol | Hold as waiting for input
2 | Avanti | Hold as waiting for input
3 | Wish leest | Hold as waiting for input
4 | Avanti | Hold as waiting for input
5 | MDN | Hold as waiting for input
7 | C P Jobsite | Hold as waiting for input

## ABBR
Abbreviation | Meaning
AM | Avinash Mishra
NJ | Nikhil Juneja
NP | Nikeshwar Pandey
MK | Muddasir Khan
ASC | Abhay singh chauhan
AS | Abnish Sharma
DG | Deendayal Gupta
HP | Hold Project
WIN | Waiting for input
WIP | Work In Progress

## Sheet5
MOM 17-Mar-2016
S.no | Project | Type | Task | Hours | From | To | Assigned | % | Status | Comment
1 | Taiga | P M T | testing and bug fixes | 6 + 8 | 2016-03-15 | 2016-03-17 | ASC | 80 | WIP | ISSUE:- 44, SOVELD:- 40,PENDING :- 4
|  |  | making production server for testing | 2 | 2016-03-16 | 2016-03-16 | ASC | 100 | done
2 | Chat App | Mobile App(Frontend) | Implementation for push notification -cold start | 4 | 2016-03-01 | 2016-03-15 | MK | 50 | WIP | After finishing “live chat user” will resolve issue of this task and integrate it into app
|  |  | Show Live chat User | 8 | 2016-03-07 | 2016-03-14 | MK | 90 | WIP | one to one chat creating problem that he is unable to create private channel for every chat user
3 | Learning | Node js | Node Js Tutorian 11 implementaion | 8 | 2016-03-17 | 2016-03-17 |  | 0 | TO DO | Still not started
|  |  | file upload | 2 | 2016-03-15 | 2016-03-15 | ASC | 10 | Hold
|  |  | Slider tutorial | 4 | 2016-03-10 | 2016-03-14 | AM | 95 | Done | Smoothness is remaing
4 | CP Job Site | Mobile App(Frontend) | fb contact List and fb Profile Page | 8 | 2016-03-10 | 2016-03-15 | AS | 100 | Done
|  |  | Google+ integration | 8 | 2016-03-16 | 2016-03-16 | AS | 100 | Done
|  |  | Twitter Integration | 8 | 2016-03-17 | 2016-03-17 | AS | 0 | WIP | Unknown provider: $cordovaOauthProvider <- $cordovaOauth
5 | Emperk | Mobile App(Frontend) | Trello 3 points | 4 | 2006-03-16 | 2006-03-16 | NP | 100 | Done
|  |  | Cossb projects setup and development | 4 | 2016-03-16 | 2016-03-16 | NP | 90 | WIP | Refinement is remaining
6 | MyStreet | Web Projects(Backend) | Resolve live issue + 5 issues | 4 | 2016-03-07 | 2016-03-16 | AM | 90 | WIP | All issue resolved except live issue